## Sheet6
Status	Bug Summary	Bug Category	Reason for slippage	Action needed to prevent slippage	Phase it should have been found in	should have been found in	Improvement recommended	EIC Installation code
CPS-2015	CPS-NCMP: DataOperationEventConsumer consumeAndPublish flooding logs with events	Logging	Missed Impact	The size of the log was way too big and in the INFO level	Review	Integration Test		X
CPS-1990	CPS-NCMP: DataOperationEventConsumer consumeAndPublish flooding logs with events	Logging	Missed Impact	The size of the log was way too big and in the INFO level	Review	Integration Test		X
CPS-1979	CPS-NCMP: CmSubscriptionNcmpInEventForwarder will send events to invalid topic	Install	Environment	Installing locally and testing it would have resulted in early detection of the bug.	Review	Integration Test		X
CPS-1977	Unable to deploy CPS with OOM charts	Install	Environment	OOM needs to be frequently updated and feedback needs to seen from the deployment and gating	Release	Integration Test		X
CPS-1958	Architecture violation when building with maven	Testware	Environment	N/A	Automated (unit) Test	Unit Testing		X
CPS-1956	CPS-NCMP: No yang resources stored during cmhandle discovery however cmhandles are in READY state	Functional	Missing requirement					X
CPS-1933	Module sync failing due to reason java.lang.ClassNotFoundException: org.onap.cps.spi.model.ModuleReference	Functional	Missing requirement	Clarification is needed on build artifacts	Microservice CI (CIST)	Integration Test	No Jira ticket	✔
CPS-1923	CPS/NCMP does not have conventional base URL for actuator endpoints	Install	Missing requirement	We just synched the url's as per the stake holders	Review	Integration Test	N/A	✔
CPS-1922	Change all actuator base endpoints of dmi-plugin to /actuator	Functional	Insufficient test coverage	Complying with Spring Boot	Review	N/A	CPS-1856	X

CPS-1913	Fix for Swagger UI	Documentation	Insufficient test coverage	Action needed to prevent slippage: Write	Release	Integration Test	CPS-1916	X
CPS-1866	intermitten ODL classnotfound exceptions when running with multiple instances	Functional	Intermittent Fault/Timing Issue	None	Microservice CI (CSIT)	Integration Test	CPS-1918	✔
CPS-1841	Update of top-level container node fails with SQL error	Functional	Insufficient test coverage	Additional test cases	Automated (unit) Test	Unit	new test added in this story	✔
CPS-1817	The root pom.xml file has an incorrect version number	Versioning/Build	Missed in code review	Avoid manual versioning of pom.xmls	Review	Pipeline build phase	Unresolved	X
CPS-1815	CPS Patch operation fails when updating parent list	Functional	Missed in design analysis	consider all relevant scenarios during design phase	Design	Integration Test		X
CPS-1813	Fix: Make bookstore data consistent	Robustness	Missed in code review	Any changes to the test data should be reviewed with equal importance	Code Review	Code Review	CPS-1586	X
CPS-1783	NCMP fails to restart due to uncaught exception saving /subscription-registry	Functional	Insufficient test coverage	additional test	Automated (unit) Test	Unit, Create top level node fails due to an AlreadyDefined exception	N/A	X
CPS-1765	CpsDataService is saving data nodes with non-normalized xpaths	Functional	Insufficient test coverage	Add additional test cases	Automated (unit) Test	Unit, Add and Delete a (container) data node	N/A	X
CPS-1758	Get Node and Query Node parse [ and ] inconsistently.	Functional	Insufficient test coverage	None (additional tests were added)	Automated (unit) Test	Unit, CpsQueryServiceSpec	Duplicate	X
CPS-1749	publishLcmEventBatchAsynchronously is not being called asynchronously	Performance	Insufficient test coverage	Update test	Automated (unit) Test	Integration test, LcmEventsCmHandleStateHandlerImplSpec	N/A	X
CPS-1716	NCMP: Java Heap OutOfMemory errors and slow registration in case of 20k cmhandles	Functional	Insufficient test coverage	Performance testing to include peak memory usage	Automated (unit) Test	Performance, Performance of CM handle registration	CPS-1753	✔
CPS-1714	NCMP: ERROR: update or delete on table \"fragment\" violates foreign key constraint \"fragment_parent_id_fkey\" on table \"fragment\	Functional	Missing requirement				Issue not reproducible	✔
CPS-1663	Contains query is broken when fetching all descendants	Functional	Insufficient test coverage	consider all relevant scenarios when writing tests (incl reviewers)	Review	Integration Test, Query for attribute by cps path using contains condition	N/A	X

CPS-1651	CpsPath Query using regexQuickFind does not return descendants with lists	Functional	Insufficient test coverage	consider all relevant scenarios when writing unit tests (incl reviewers)	Review	Unit, Cps Path queries with all descendants including descendants that are list entries	N/A	X
CPS-1629	Ordering of leaf elements to support combination of AND/OR in cps-path	Functional	Missing requirement	Precise test	Design/Review	Unit test, wherein querying a specific cps path ending on a list with operators OR and AND, the test checks that the storing of operators in a map is correctly ordered for the call	N/A	X
CPS-1628	Kafka Headers not populated with intended properties	Functional	Missing requirement (unclear requirement)	Better use of Wiki pages for detailing requirements and focus on content rather then format i.e. no 'annotated' json examples but rather clear tables with details for each field	Integration Test	Integration Test, message has correct header(detail)s		X

CPS-1626	NCMP: java.lang.NoClassDefFoundError: org/apache/commons/collections4/CollectionUtils	NO FSA done					Issue not reproducible	✔
CPS-1625	Onap Registry Pull Limit for Test Container cp-kafka	Install	The reason is not clear, however it could be pull limit in docker registry.	The version of the test containers aligned with CPS	Automated (unit) Test	Unit, The issue is intermittent and non reproduceable.	Unresolved	X

CPS-1607	Correct documentation for GET node API	Documentation	Missed in document review	double checking URL links on code reviews	Review	Review	N/A	X
CPS-1568	Unable to upgrade using Spring Application Events approach	Install	Intermittent Fault/Timing Issue	Test on other client's environments	Review	Integration Test, This should have been tested on different environments and in cases where database is not set up properly yet		X

CPS-1566	NCMP pods unable to form distributed cache cluster	High Availability	Environment	we could have tested in the k8s environment with multiple instances	Microservice CI (CIST)	Performance, The problem arises when we have multiple instances and we use kubernetes environment. The cluster members were unable to discover each other. We made relevant enhancements to make this working.		X

			Functional = 21
			LOGGING = 1
			INSTALL = 6
			DOCUMENTATION = 4
			Robustness = 1
			Performance = 3
			Testware/CI = 3
			High Availability = 1
			NO FSA done =3
			Versioning/Build = 1