## Slide 1: DCAE Weekly Meeting
2019-04-11

## Slide 2: Dublin Schedule
RELEASE MILESTONE
M1- 01/16-01/24
M2 - 02/21*
M3 -03/14
M4 - 04/04 (04/11)
RC0 - 4/25
RC1 - 05/09
RC2 - 05/23
05/30 - Release sign off
Notes: RELEASE MILESTONE M1- 01/16-01/24 M2 - 02/21 M3-03/14 1-week; M4 - 04/04 RC0 - 4/25 RC1 - 05/09 RC2 - 05/23 05/30 - Release sign off

## Slide 3: DCAE R4 M4 Status
  https://wiki.onap.org/display/DW/DCAE+R4+M4+Code+Freeze+Milestone+Checklist
  https://wiki.onap.org/display/DW/Project+Status+in+Dublin+Release
  Dashboard
  Dmaap plugin integration/test
  Jenkins job (3/160+) failing
  CSIT (https://jenkins.onap.org/view/CSIT/job/dcaegen2-collectors-datafile-master-csit-Functional-suite/)
  Sonar (20/20)
  Pending updates
    SON-Handler – Policy Update flow
    ?
  On-demand/Dynamic deployment steps
  https://wiki.onap.org/display/DW/DCAE+R4+Service+Component+%28On-demand%29+deployment+Instruction

## Slide 4: OOM – charts/values
Note: OOM to have only released images post RC0

## Slide 5: DCAE Committer updates
Committer role extensions (to additional DCAE repositories) - Jaszczyk, Piotr & Wielebski, Piotr
https://wiki.onap.org/display/DW/Committer+Extension+Request+for+%5BDCAE%5D%3A+Piotr+Jaszczyk
https://wiki.onap.org/display/DW/Committer+Extension+Request+for+%5BDCAE%5D%3A+Piotr+Wielebski
New committer promotions - Henrik Andersson B & Murgoski, Zlatko
https://wiki.onap.org/display/DW/Committer+Promotion+Request+for+%5BDCAE%5D%3A+Henrik+Andersson
https://wiki.onap.org/display/DW/Committer+Promotion+Request+for+%5BDCAE%5D%3A+Zlatko+Murgoski
Notes: From Jessica to Everyone: 09:27 AM
https://jenkins.opendaylight.org/releng/view/odlparent/job/odlparent-maven-stage-3.1.x/
From Jessica to Everyone: 09:35 AM
https://jenkins.onap.org/job/ccsdk-utils-maven-stage-master/4/console
Maven-staging-plugin - nexus-staging-maven-plugin:1.6.7:deploy
Nexus2 migration ticket: https://jira.onap.org/browse/CIMAN-234

## Slide 6: F2F – El Alto Updates
Release timeline change
Security (java script coverage)

## Slide 7: ONAP Timeline Evolution – El Alto
8w 4w 3w 4w 2.5w 2w 3w 1w
El Alto
M3
APIs
Freeze
Sign Off & Release
M4
Code
Freeze
M2
Functionality
Freeze
M1
Planning
Freeze
Scope Def. & Design
Development
RC2
Tests and bug fixes
RC0
RC1
M0
Kick-Off
Require Significant Code Changes (>4 Weeks)
Use Cases
Functional and Non-Functional Requirements
1
1W 4W 4 W 1W
E1 Release Candidate
E2
E3
10 W
Dev E1
Test E1
Rel. E1
Limited Code Change (Max. 4 weeks)
No or limited cross-applications dependency
Non-Functional Requirements (Security/Vulnerability issues, Code Optimization, Sev2 Defect Backlog Reduction, etc.)
PTL Enhancements
Documentation Enhancements
E1-3 Release Candidates
included in El Alto Release until Release Code Freeze
Def. E1
Dev E2
Test E2
Rel. E2
Def. E2
Dev E3
Test E3
Rel. E3
Def. E3
5 W
5 W
...

## Slide 8: ONAP Release cycle Evolutions
ONAP Releases Timeline/focus
  El-Alto release - ~4 months (June-Sept)
    Maintenance
    Project back logs
  Frankfurt release (Extended planning, but release 1Q20)
Edge Automation – ARC Next Steps
  Requirement clarification to be finalized by 04/16/2019
  Finalized Architecture Presentation to Arch. Sub Committee on 04/23/2019

## Slide 9: El-Alto Items (Deferred from Dublin)
  SEC-COM Open items
    Secure communication
      Topic/feed
      CBS (dependency on Consul)
    Non-root container
    Security Vulnerability (review Dublin exception list and close)
  CIA
  S3P
    Documentation/Usability
    Performance test/bench-marking (such as response time, transaction/message rate, latency, footprint, etc. to be defined on per component)
    Application logging consistency (Manageability)
    API Standardization (Usability)
  Jenkins job alignment (moving to common template)
  CSIT improvement
  Platform components (security/csit/jjb)
  Blueprint generator/Dmaap plugin integration
    (Topic standardization – pre-requisite)
  SDK library integration (Except PRH/HV-VES)
  Policy Integration for dynamic components

## Slide 10: Acumos-ONAP Integration Phase 1 Process Steps (3Q 2019)
Describe the Use Case of a ML-assisted ONAP Control Loop that provides values to Operations
Acumos designer onboard a ML model that contains sufficient data to support ONAP DCAE/CL in Design time & Runtime.
Acumos distributes the ML model to ONAP via E5 federation.
ONAP E5 Receiver uses µS Adaptor to transform and onboard into SDC catalog as Analytic µS.
ONAP user selects the ML Analytic µS into a DCAE flow template and attaches to a service (SDC/DCAE-DS). A blueprint is auto-generated* and distributed to CLAMP & DCAE-C.
ONAP user uses CLAMP to further configure an operational policy to fix the problem as identified by the ML Analytic µS.
ONAP user deploys the CLAMP blueprint to implement the control loop.
Overtime the collected network data will be used to enhance & retrain the ML model.
New
Work
ONAP
BAU
Process
*broken in ONAP Casablanca release

## Slide 11: Acumos-ONAP Integration Phase 1 Dataflow (3Q 2019) Demonstrate with a Control Loop Use Case
ONAP µS Adaptor
ONAP
Acumos
Acumos Catalog
DCAE Docker Generation
Docker Repository accessible from DCAE environment where you are deploying into
Generate
DCAE MS Metadata (DCAE component spec + Data format)
SDC Catalog
url reference
VNF
VNF
Analytic MS
Tosca Format
SDC/DCAE-DS
DCAE Blueprint
VNF
Collector
MS
Analytic
MS
DCAE Deployment
MANUALLY DEPLOYED
VNF
Collector
MS
Analytic
MS
Onboard ML model & validate it has all data required by ONAP DCAE µS
CLAMP Design GUI
Analytic
MS
Policy
Policy
Repo
Collector
VNF
DCAE Blueprint
VNF
Collector
MS
Analytic
MS
Policy
11
SDC Tosca Tool
DCAE-CLI validation
Acumos
Federation
µS in Tosca Format
DCAE
Runtime
Pub
Acumos
ML Model
SDC Blueprint Generator
New Work
Existing SDC/DCAE tools
2018 ONS POC
(with modifications)
Legend
Sub
DCAE
Runtime Registry
Identify a real Operations problem
Develop & train a ML model with ONAP production data
Data Lake
VNF
1
2
3
4
5
6
7
8