## Slide 1: SDC enhancement - CCVPN Coding work status
April 1, 2019

## Slide 2: Schedule
Coding work item | Status | Mar 18 |  |  |  |  | Mar 25 |  |  |  |  | Apr 1 |  |  |  |  | Apr 8 |  |  |  |  | 
 |  | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 13
UI/Front-end(Design, Implement, Test) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UI view/Layout | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Properties tab, Input tab | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Declare List Input dialog | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Document review, Code review | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Back-end(Design, Implement, Test) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Defile internal data(Design) | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Define REST parameter(Design) | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Create (Declare List Button) | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Get(showing properties and inputs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Delete(trash icon in Input tab) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Generating CSAR | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Document review, Code review | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TOSCA Parser |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Studying and Considering | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Support parsing new get_input | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Document, review, Code review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Submit , SONAR check |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rev
Code review
Code review
Doc
Rev
Doc
Code review
Two staffs
One staff
One staff
M4 code freeze is postponed to April 11
coding:0%, test:0%
coding:20%
coding:20%
coding:30%, test:5%
coding:40%, test:10%

## Slide 3: Status and risk
Status
  UI: New layout design/implementation of SDC GUI is completed. The implementation of property-tab, input-tab and declare is started.
  Back-end: Design of internal data of the back-end and design of REST between front-end and back-end are in completed and start implement.
  TOSCA parser: Studying and consideration of the changes are done, Coding is just started.
Risk
  The back-end change work may be delayed because it is complex and difficult.