## Slide 1: SDC enhancement - CCVPN Coding work status
April 8, 2019

## Slide 2: Schedule
Coding work item | Status | Mar 18 |  |  |  |  | Mar 25 |  |  |  |  | Apr 1 |  |  |  |  | Apr 8 |  |  |  |  | 
 |  | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 13
UI/Front-end(Design, Implement, Test) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UI view/Layout | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Properties tab, Input tab | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Declare List Input dialog | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Document review, Code review | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Back-end(Design, Implement, Test) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Defile internal data(Design) | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Define REST parameter(Design) | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Create (Declare List Button) | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Get(showing properties and inputs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Delete(trash icon in Input tab) | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Generating CSAR | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Document review, Code review | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TOSCA Parser |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Studying and Considering | Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Support parsing new get_input | In progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Document, review, Code review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Submit , SONAR check |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rev
Code review
Code review
Doc
Code review
M4 code freeze was postponed to April 11
coding:100%, test:0%
coding:20%
coding:100%
coding:100%, test:10%
coding:100%, test:20%
Plan
Actual
coding:100%, test:10%

## Slide 3: Status and risk
Status
  Implementations of UI/Front-end, Back-end, TOSCA parser have almost finished.
  JUNIT testing is in progress now.
  Code submission will be April 10. (Can we submit code before test is complete? If yes, we will submit the code on April 9)
Risk
  The back-end change work may be delayed because it is complex and difficult. (何鹏 who is expert of back-end in CCVPN team will help us if we have technical questions)